## Sheet1
Monitoring Objective and Short Description | Research Potential | Focus | Driver | Timing & Duration | Interested or Responsible Party(ies) | Partner(s) | Funding | Principal Contact | Secondary Contact (if applicable)
Ongoing
Ecology / fish / macroinvertebrates / crayfish / food base and trophic positions | yes | riparian/stream corridor | science, regulatory, adaptive management | work continuing, and much of it should continue for at least 10 years | NAU (Jane Marks) & USFWS (Pam Sponholtz/Shaula Hedwall) | USFS | in-place, proposed | Jane Marks, NAU, Box 6024, Flagstaff, AZ 86011 (928) 523-0918 | Pam Sponholtz/Shaula Hedwall: USFWS, 323 N. Leroux, Flagstaff, AZ 86001 (928) 226-0614
Travertine formation | yes | riparian/stream corridor | science, regulatory | summer 2004 and into full flow cycle | NAU (Rod Parnell) |  | in-place, proposed | Rod Parnell, NAU, Box 4099, Flagstaff, AZ 96011 (928) 523-3329
Recreation use and impacts | yes | riparian/stream corridor | adaptive management | start summer 2004 through return of full flows | NAU (Marty Lee) | USFS | in-place | Marty Lee, NAU,Box 15018, Flagstaff, AZ 86011 (928) 523-6644
Cultural and Archeological Resource Impacts | yes | Childs-Irving facilites | regulatory | 2005-2009 | APS/USFS/SHPO |  | N/A | APS
Spring Discharge and Characterization | yes | riparian corridor, watershed | science, management | start summer 2004 | NAU (Abe Springer) |  | in-place | Abe Springer, NAU, Box 4099, Flagstaff, AZ 96011 (928) 523-7198
Channel morphology and sediment distribution | yes | riparian corridor, watershed | regulatory, science, adaptive management | Begin summer/fall 2004 and continue thorugh at least 2010 | NAU (Charlie Schlinger) |  | in-place, proposed | Charlie Schlinger, NAU, Box 15600, Flagstaff, AZ 86011 (928) 523-0652
Leopard frogs | yes | riparian corridor | science, regulatory, and adaptive management | summer 2004 through 2009 | USFWS (Shaula Hedwall) / USFS (Cecelia Overby, Janie Agyagos, Justin Jimenez, Susi MacVean & Mike Sredl at AZ Game & Fish) |  | unknown | Cecilia Overby, USFS, Coconino National Forest, Flagstaff, AZ (928) 527-3460 | Shaula Hedwall,USFWS, 323 N. Leroux, Flagstaff, AZ 86001 (928) 226-0614
Riparian vegetation | yes | riparian corridor | regulatory, adaptive management | 2004 and 2007 | USFS/ USFWS |  | unknown | Janie Agygos: USFS, Red Rock Ranger District, (928) 203-7507 | Pam Sponholtz/Shaula Hedwall: USFWS, 323 N. Leroux, Flagstaff, AZ 86001 (928) 226-0614
In-stream habitat (pools, riffles, travertine dams) | yes | stream | science, adaptive management | 2004 through return of full flows | USFS/USFWS/AGFD/NAU |  | ??? | Janie Agygos: USFS, Red Rock Ranger District, (928) 203-7507 | Pam Sponholtz: USFWS, Flagstaff Suboffice, 323 N. Leroux, Flagstaff, AZ 86001 (928) 226-0614
Watershed headwater areas | yes | watershed | science, management | prior 2004 and 2004 | NAU: Jane Marks (water quality and macroinvertebrates)/Dianne Anderson (long-term sediment history along M. Rim |  | in-place | Jane Marks, NAU, Box 6024, Flagstaff, AZ 86011 (928) 523-0918
Ecosystem processes (decomposition, primary productivity, travertine formation, nutrient cycling, microbial genetics) | yes | riparian/stream corridor/watershed | research/adaptive management |  | NAU (Marks, Watwood, Parnell, Hungate) |  | in-place, proposed | Jane Marks, NAU, Box 6024, Flagstaff, AZ 86011 (928) 523-0918 | Rod Parnell, NAU, Box 4099, Flagstaff, AZ 96011 (928) 523-3329
Spring water chemistry (minor, trace, and gases) | yes | riparian/stream corridor/watershed | science, management | Summer and Fall 2004 | NAU (Abe Springer)/UNM |  | in-place, proposed | Abe Springer, NAU, Box 4099, Flagstaff, AZ 86011 (928) 523-7198
Yellow-billed cuckoo, wouthwestern willow flycatcher, black hawk surveys | yes | riparian corridor/watershed | science, management | summer 2004 through 2009 | USFS and FERC (flycatcher)/USFS (Janie Agyagos) (cuckoo and hawk) |  | separate Heritage Grant (USGS) for 2004/funding beyond this year not secured yet | Janie Agyagos: USFS, Red Rock Ranger District, Sedona, AZ (928) 203-7507
Northern Gila County regional geologic mapping and water testing monitoring | possibly | watershed | science, adaptive management | ongoing; anticipated completion by mid-2005 | USBR (Leslie Meyers) |  | in-place | Leslie Meyers, U.S. Bureau of Reclamation, (602) 216-3835
Native fish renovation and monitoring (fish and macroinvertebrates) | yes | stream corridor/watershed | science, adaptive management | October-December 2004 | AGFD (Dave Weedman) - lead / USFWS (Pam Sponholtz/Shaula Hedwall) / USBR (Rob Clarkson) / USFS (Cecilia Overby); USFS Rocky Mountain Research Station (Steve Overby); NAU (Jane Marks) | AGFD, USFWS, USBR, NAU | in-place | Dave Weedman, AGFD, Mesa office, 480-324-3545 | Pam Sponholtz/Shaula Hedwall: USFWS, Flagstaff Suboffice, 323 N. Leroux, (928) 226-0614
Aerial Photography Mission/Remote Sensing | yes | riparian corridor/watershed | science | summer 2004, November 2004 | NAU (Charlie Schlinger) | Cooper Aerial | summer 2004 by Cooper; USFS may fly in 2005 | Charlie Schlinger: NAU, Box 15600, Flagstaff, AZ 86011 ((28) 523-0652
Cultural/Archeological Resources | possibly | riparian/stream corridor/watershed | management | Historic Properties Mgmt. Plan completed and accepted by SHPO | APS | Coconino National Forest, Red Rock Ranger District; SHPO | in-place | Phil Smithers, APS | Ken Anderson, Red Rock District Ranger, Sedona (928) 203-7501
Cultural/Archeological Resources | possibly | riparian/stream corridor/watershed | management | 2005-2010 | Yavapai-Apache Nation |  | in-place | Chris Coder, Yavapai Apache Nation, ccoder@yan-tribe.org, 928-567-7026
Landscape-Scale Assessment of Fire Risk | yes | watershed | regulatory, adaptive management | Ask Haydee Hampton | NAU (Haydee Hampton) | USFS | in place (part of larger project) | Haydee Hampton, NAU, P.O. Box 5694, Flagstaff, AZ 86011 (928) 523-0872
Stehr Lake sediment coring | yes | watershed | science | summer 2004 | NAU (Paul Gremillion) |  | in-place (NAU funded) | Paul Gremillion, NAU, Box 15600, Flagstaff, AZ 86011 (928) 523-5382
Streamflow Gaging | yes | stream, watershed | science, management, adaptive management | on-going | USFS |  | Tonto N.F. is funding quarterly gaging | Grant Loomis: Tonto N.F., Phoenix, AZ
Streamflow Gaging Station | yes | stream, watershed, region | science, management, adaptive management | 2005-2006 | NAU, SRP, USFS, USBR |  | NAU proposal for gaging station site selection and design has received approval from SRP | Charlie Schlinger: NAU, Box 15600, Flagstaff, AZ 86011 ((28) 523-0652; Greg Kornrumph, P.O. Box 52025, SRP, Phoenix, Arizona 85072-2025, 602-236-3264 | Leslie Meyers, U.S. Bureau of Reclamation, (602) 216-3835; Grant Loomis: Tonto N.F., Phoenix, AZ